## Sheet1
Description of Risk | Cause | Risk Event | Impact | Rating | Action
Time management | Not giving enough time to each task | Not being able to hand in a fully executable code | 4 | 7 | Setting small goals on a weekly basis to go through whatever you do not understand
Lack of Knowledge | Not knowing enough of the programming language to complete certain tasks | Completion of project | 4 | 7 | Setting small goals on a weekly basis to go through whatever you do not understand
Self discipline | Not starting quicker | Important parts of project missed | 3 | 8 | Having small breaks to ensure I am on task
Loss of time | COVID-19 | Not being able to use all the tools required | 5 | 9 | Global pandemic
Unreliable application | Not enough tests, need to make it more secure for client ot be able to use. | Not garunteed to work | 2 | 6 | Testing on specific and well reliable code
Poor Change Management | Using GitHub to actively manage project version control and pushing work to the repository once a week or more. | Using an effective version control tool to reduce chances for poor change management. | 4 | 6 | GitHub version control has been used and represents an effective repository of all useful documents.
Lots of Computer Working | Using proper equipment and taking short, frequent breaks to move about will minimize the associated health risks | Being wary of the health risks of computer working and taking steps to avoid them. | 3 | 5 | Good computer working practice has mostly been adhered to but some discomfort was experienced at the end of the project when hours were long and breaks were infrequent.
Illness or other unforseen absence | Illness/ unforseen absence would reduce available time to work on the project and would contribute to project delays. |  | 1 | 4 | The likelihood of unforseen absence is hard to reduce but the impact can be mitigated by good planning.